## CDT-Africa Plan 2012 E.C
EASTERN AND SOUTHERN AFRICA CENTERS OF EXCELLENCE (ACE II)
Name of the ACE: |  | Center for Innovative Drug Development and Therapeutic Trials for Africa (CDT-Africa) | [7 empty] | Budget Year 2012 E.C, 2019/20 G.C
July 08 2019 - July 07 2020
Component | Sub- component | Action Plan | Objective | Justification | Output | DLI # | DLR # | Estimated Budget (US$) | Responsible Unit | Hamle/ July | Nehase/ August | Meskerem/ September | Tikimt/ October | Hidar/ November | Tahisas/ December | Tir/ January | Yekatit/ February | Megabit/ March | Miyazia/ April | Ginbot/ May | Sene/ June
Component: Strengthening CDT-Africa Center of Excellence
|  | Sub-component 1: Well functioning CDT-Africa Consortium | [5 empty] | 285500
|  | 1.1. Effect salary of existing and new staff of the Center | Staff required to execute day to day activities of the Center | The Center has employed essential staff to support the teaching and research tasks of CDT-Africa. Additional staff staff for the Bio-Hub, Data Manager, Data Entry Clerks and Admin staff. | Having a well staffed Center to deliver on key objectives of CDT Africa | 1 | 1.1 | 120000 | Lead, Tech, Admin | X | X | X | X | X | X | X | X | X | X | X | X
|  | 1.2 Setting up additional office spaces of the Center | To have additional well-organized and functional office space | The Center's existing office space is too small to accommodate all staff and faculty. Thus, the Center plans to secure additional office spaces in AAU and renoviate, refurbish and furnish accordingly. | Additional refurbished office spaces of CDT-Africa | 1 | 1.1 | 100000 | Lead, Tech, Admin | X | X | X | X | X | X
|  | 1.3 Regularly update the Center's website and server maintenance | To regularly communicate status of the Center and use as platform for transfer of scientific knowledges | The website is proved to be an essential platform for information exchange about the CDT-Africa. An expert will be assigned on part-time bases for this task. | Center website updated regularly | 1 | 1.1 | 5000 | Lead, Tech | X | X | X | X | X | X | X | X | X | X | X | X
|  | 1.4 Design and sign additional MOUs with partners | To identify and signadditional MoUs with potential national and international partners for collaborative undertakings | The Center needs more collaborating institutions to effectively attain it's objectives | Signed MoUs | 1 | 1.1 | 500 | Lead, Tech | X | X | X | X | X | X | X | X | X | X | X | X
|  | 1.5 Host annual consortium meeting | CDT-Africa plans to conduct an annual consortum meeting with is partners to update status of the Center and plan activities | CDT-Africa needs to obtain direction from its consortum members for effectiveness | Feedback and plan | 1 | 1.1 | 25000
|  | 1.6 Staff development | To strengthen capacity of the Center through capacity development of its staff | Capacity of existing staff needs to be strenthened for effectiveness of the Center | No. of staff gaps identified and capacity developed through training, exchange visits, mentorships | 1 | 1.1 | 20000
|  | 1.7 Maintenance of vehicles cost, Fuel & lubricants | To standby CHS's vehicles for the Center | The Center's vehicles used for office use and to transport students need to have fuel, lubricants, and maintenance for effective use | Uninterrupted transport services | 2 | 1.1 | 15000 | Admin | X | X | X | X | X | X | X | X | X | X | X | X
|  | Sub-component 2: Learning excellence | [5 empty] | 322000
|  | 2.1 Learning facility upgrades - Refurbish additional smart classrooms - Refurbish additional dormitories | To improve learning facilities and dormitories | Upgrading learning facilities and dormitories of students is required toenhance learning experience of the center | 6 learning facilities and 12 dormitories upgraded and a conducive teaching-learning environment created | 1 | 1.1 | 10000 | Lead, Admin, Tech | X | X | X | [7 empty] | X | X
|  | 2.2 Delivery of short courses - Advertise the short courses - Select trainees - Recruit trainers - Prepare training materials and space - Arrange housing and catering for trainees - Manage travel expense for trainees and visiting professors | To deliver short-term courses essential for medicines advancements | CDT-Africa will deliver short courses (the following courses are provisionally listed as important priorities: 1) Health Research Ethics and Good Clinical Practice, 2) Trial Monitoring, 3) DSMB and Good Laboratory Practice, 4) Genetics/Genomics, and 5) Clinical Trials Methodology. | 102 trainees completed short courses: 74 National [50 Female, 24 Male], 28 Regional [10 Male, 18 Female] | 2 | 2.2 | 12000 | Tech | X | X | X | X
|  | 2.3 Ongoing PhD/Postdoctoral students' support | To support ongoing PhD/Postdoctoral students/fellows already enrolled. | CDT-Africa has 23 PhD/Postdoctoral students/ fellows enrolled and need ongoing support. | 23 PhD/Postdoctoral Students [21 National (18 M, 3 F), 2 Regional (2 F)] supported, their research supervised. | 2 | 2.2 | 55000 | Lead, Tech, Admin | X | X | X | [6 empty] | X | X | X
|  | 2.4 Ongoing MSc students support | To support ongoing MSc students already enrolled. | CDT-Africa has 25 MSc students enrolled within existing programs of CHS AAU. | 25 MSc Students [20 National (10 M, 10 F), 5 Regional (3 F, 2 M] supported. | 2 | 2.2 | 65000 | Lead, Tech, Admin
|  | 2.5 Enrolment of MSc & PhD/Postdoctoral students Advertisment, Selection, Enrolment, run programs) | To enroll students in MSc in Clinical Trial, PhD in Translational Medicine, and postdctoral in cross-cutting programs. | CDT-Africa focuses on increasing human resources capacity for medicine innovations regionally. As part of this effort, the Center aims to enrol up to 50 students (28 MSc, 16 PhD, 6 Postdoc. | Enrolment of 16 PhD Students [11 National (4 M, 7 F), 5 Regional (1 M, 4 F)] Enrolement of 28 MSc students [18 National (9 M, 9 F), 10 Regional (10 F)] Enrolment of 6 postdoctoral fellows [3 M, 3F] | 2 | 2.2 | 150000 | Lead, Tech, Admin | X | X |  |  |  | X | X | X | X | X | X | X
|  | 2.6 Faculty and PhD students exchanges | To promote research and teaching at CDT-Africa and CHS AAU at large | PhD students and the CDT-Africa/CHS faculty neeed to learn from and adapt medicine development, advance clinical trials and leadership skills to apply in their acedemic, research and leadership activities | 20 exchanges for CDT-Africa/CHS faculty and students | 2 | 2.6 | 30000 | [7 empty] | X | X | X | X | X | X
|  | Sub-component 3: Research Excellence | [5 empty] | 762000
|  | 3.1 Initiate medical discovery and development research projects, preferrably linked to capacity building. | To initiate research projects in an area with clear gap of knowledge on treatment, diagnostics, vaccines, or complex interventions. | The projects will enhance development of medicines, vaccines, diagnostics, or complex interventions. The projects will offer opportunity for capacity building. | Two medical discover/development projects initiated and their major preparatory steps undertaken; four grant applications submitted | 2 | 2.5 | 50000 | Lead, Tech | X |  | X |  |  |  | X
|  | 3.2 Conduct confirmational pre-clinical study on promising herbal products - Procure reagents, chemicals and animal models - Conduct relevant confirmatory study on animal models | To confirm safety, efficacy and kinetics of herbal products | Conducting conformational tests on animal models is needed to confirm safety, efficacy and kinetics of the product, with preliminary information confirmed and available for translational work and further development including clinical trials in humans. | 3 herbal products made available for further development including clinical trials in humans. | 2 | 2.5 | 10000 | Lead, Tech | X | X | X | X | X | X | X | X | X | X | X | X
|  | 3.3 Support product development through the innocafe (Incubation hub) and small grants initiatives | To support new product development through potential applicants approaching CDT-Africa or through CDT-Africa initiated adverts | Supports to young scholars and PhD students as well as mature scientists is needed to develop new products. | 3 incubatee for up to three potential products come to early stage development | 2 | 2.5 | 50000 | Lead, Tech, Admin | X | X | X | X | X | X | X | X | X | X | X | X
|  | 3.4 Procure laboratory equipment, reagent and supplies necessary for conducting clinical trials and therapeutic development studies | Organize a state of the art CDT-Africa laboratory capable of hosting advanced clinical trial and medicinal development studies | Organizing a state of the art lab is needed to conduct clinical trials and medicinal studies potential for drug, diagnostic and vaccine developments. | Clinical trials and medicinal development studies are underway and some outcomes presented in conferences | 2 | 2.5 | 650000 | Lead, Tech, Admin | X | X | X | X | X | X | X | X | X | X | X | X
|  | 3.5 Publish research finding in reputable journals | Inform scientific outcomes and global reachability of the Center. | The Center needs to publish study findings to contribute to development of medicines at national, regional, and global levels | At least 70 articles focusing on medicine discovery and development, including complex interventions, published in peer-reviewed journals | 2 | 2.5 | 2000 | Lead, Tech | X | X | X | X | X | X | X | X | X | X | X | X
|  | Sub-component 4: Quality assurance | [5 empty] | 81100
|  | 4.1 Quality benchmarking - Identify centers to benchmark - Contact centers and arrange for visit - Conduct site visit - Implement changes - Also explore rrequirements for PASET benchmarking | To adapt implementation according to benchmarked standards | Ensuring quality assurance requires benchmarking international centers thereby developing implementation framework and standardize accordingly. | 3 international centers visited and benchmarked, framework for implementation developed and standardized for CDT-Africa | 2 | 2.8 | 60000 | Lead, Tech, Admin | X | X | X | [6 empty] | X | X | X
|  | 4.2 Host scientific advisory board and public advisory board meeting - Communicate with Board Members - Secure accommodation for regional and international members - Agree agenda of Meeting - Hold Meeting | To obtain scientific and administrative inputs for the Center | These meetings are required to obtain input on the scientific merit and required improvements on the implementation of CDT-Africa and to obtain public buy-in and accountability of CDT-Africa, and to obtain inputs from the public regarding environmental impact | Obtain guidance and feedback from the boards (bi-annual for each board) | 1 | 1.1 | 15000 | Admin |  |  | X |  |  | X |  |  | X |  |  | X
|  | 4.3 Monitoring and evaluation | Monitor and evaluate activities of the Center based on the Center's monitoring and evaluation framework | Continuous monitoring and evaluation of the Center's activities is needed for achieving the objectives of the Center | The Center adhered strictly to best financial, procurement, monitoring and evaluation practices during the entire project | 1 | 1.2 | 6000 | Lead | X | X | X | X | X | X | X | X | X | X | X | X
|  | 4.4 Obtaining national accreditation | To obtain national accreditation of one PhD curriculum | The program's PhD curriculum in Translational Medicine needs to obtain national accreditation | The curriculum is recognized and approved by MOSHE. | 2 | 2.3 | 100 | Lead, Tech |  |  | X
|  | Sub component 5: Strengthen education & research capacity | [5 empty] | 23000
|  | 5.1 Support faculty to submit major grant applications | To support CDT-Africa and AAU faculty for grant application | The faculty's capacity to developing and submitting grants need to be strengthened; this will also ensure sustainability of CDT-Africa | 2 suitable proposals developed and submitted to donor agencies or potential private sector, and at least one proposal funded | 2 | 2.7 | 20000 | Lead, Tech | X | X | X | X | X | X | X | X | X | X | X | X
|  | 5.2 Raise revenue from external sources | To sustain CDT-Africa through raising revenue from external resources | Generating external revenue is critical to ensure sustainability of programs and projects under the CDT-Africa | 4 external revenue generated | 2 | 2.7 | 3000 | Lead, Tech, Admin | X | X | X | X | X | X | X | X | X | X | X | X
|  | Sub component 6: Adhere to best financial management practice | [5 empty] | 8700
|  | 6.1 Prepare and submit annual financial report | To establish a sound financial system | CDT-Africa need to establish a sound financial system that meets all international best practices | Two financial reports submitted by the end of the year. | 3 | 3.1 | 200 | Admin | [5 empty] | X | [5 empty] | X
|  | 6.2 Ensure transparency in financial management - Publish budgets, annual work plans, audit reports, and financial reports on AAU/CDT-Africa website by Months 6 & 12 of the project year | To ensure a sound financial system that meets international best practices | CDT-Africa need to ensure transparency in financial management by uploading budget, annual work plan, audit reports, and financial management plan on its website | Restrictive web-accessible audit and financial reports, annual work plan, and budgets | 3 | 3.4 | 500 | Admin | X | X | X | X | X | X | X | X | X | X | X | X
|  | 6.3 Ensure internal/External audit oversight - Engage AAU internal audit unit in all financial procedures and transactions. Includes employment of an internal auditor to support CDT-Africa and the College of Health Sciences | Ensure CDT-Africa has internal audit oversight in collaboration with Addis Ababa University | An inclusive internal auditing of the project needs to be conducted at the end of month 12, engaging the AAU internal audit unit. The AAU Finance Directorate will follow due diligence at all stages of the audit. | The internal audit office of AAU conducted inclusive auditing at the end of month 12. | 3 | 3.3 | 8000 | Admin | [11 empty] | X
|  | Sub component 7 : Ensure best procurement practice | [5 empty] | 7000
|  | 7.1 Undertake third-party procurement processes verification | To ensure the enter has a verified procurement process. | CDT-Africa's procurement procedures need to be verified by a third party. | The Center's procurement procedures verified by a third-party. | 4 | 4.2 | 4000 | Admin | [5 empty] | X | X |  |  |  | X | X
|  | 7.2 Ensure timeliness of procurement process | To ensure availability of sound procurement procedures that meet all international standards | Automated procurement procedure in place | Timeliness of all procurement processes and transactions | 4 | 4.1 | 3000 | Admin | X | X | X | X | X | X | X | X | X | X | X | X
|  | Total Component Budget | [5 empty] | 1489300
|  | Contingency (5%) | [5 empty] | 74465
|  | Grand total Budget | [5 empty] | 1563765
NB: Lead: Center Leadership Unit; Tech: Center Technical Unit; Admin: Center Administration and Operation Unit