## CDT-Africa Plan 2011EC
EASTERN AND SOUTHERN AFRICA CENTERS OF EXCELLENCE (ACE II)
Name of the ACE: |  | Center for Innovative Drug Development and Therapeutic Trials for Africa (CDT-Africa) | [7 empty] | Budget Year 2011 E.C, 2018/19 G.C
July 08 2018 - July 07 2019
Component | Sub- component | Action Plan | Objective | Justification | Output | DLI # | DLR # | Estimated Budget (US$) | Responsible Unit | Hamle/ July | Nehase/ August | Meskerem/ September | Tikimt/ October | Hidar/ November | Tahisas/ December | Tir/ January | Yekatit/ February | Megabit/ March | Miyazia/ April | Ginbot/ May | Sene/ June
Component: Strengthening CDT-Africa Center of Excellence
|  | Sub-component 1: Well functioning CDT-Africa Consortium | [5 empty] | 179000
|  | 1.1. Effect salary of existing and new staff of the Center | Staff required to execute day to day activities of the Center | The Center has employed essential staff to support the teaching and research tasks of CDT-Africa. Additional staff staff for the Bio-Hub, Data Manager, Data Entry Clerks and Admin staff. | Having a well staffed Center to deliver on key objectives of CDT Africa | 1 | 1.1 | 120000 | Lead, Tech, Admin | X | X | X | X | X | X | X | X | X | X | X | X
|  | 1.2 Setting up additional office spaces of the Center | To have additional well-organized and functional office space | The Center's existing office space is too small to accommodate all staff and faculty. Thus, the Center plans to secure additional office spaces in AAU and renoviate, refurbish and furnish accordingly. | Additional refurbished office spaces of CDT-Africa | 1 | 1.1 | 50000 | Lead, Tech, Admin | X | X | X | X | X | X
|  | 1.3 Regularly update the Center's website | To regularly communicate status of the Center and use as platform for transfer of scientific knowledges | The website is proved to be an essential platform for information exchange about the CDT-Africa. An expert will be assigned on part-time bases for this task. | Center website updated regularly | 1 | 1.1 | 3000 | Lead, Tech | X | X | X | X | X | X | X | X | X | X | X | X
|  | To identify and sign additional MoUs | To identify and signadditional MoUs with potential national and international partners for collaborative undertakings | The Center needs more collaborating institutions to effectivly attain it's objectives | Signed MoUs | 1 | 1.1 | 1000 | Lead, Tech | X | X | X | X | X | X | X | X | X | X | X | X
|  | Host annual consortium meeting | CDT-Africa plans to conduct an annual consortum meeting with is partners to update status of the Center and plan activities | CDT-Africa needs to obtain direction from its consortum members for effectiveness | Feedback and plan | 1 | 1.1 | 20000
|  | Staff development | To strengthen capacity of the Center through capacity development of its staff | Capacity of existing staff needs to be strenthened for effectiveness of the Center | No. of staff gaps identified and capacity developed through training, exchange visits, mentorships | 1 | 1.1 | 20000
|  | 1.5 Maintenance of vehicles cost, Fuel & lubricants | To standby CHS's vehicles for the Center | The Center's vehicles used for office use and to transport students need to have fuel, lubricants, and maintenance for effective use | Uninterrupted transport services | 2 | 1.1 | 5000 | Admin | X | X | X | X | X | X | X | X | X | X | X | X
|  | Sub-component 2: Learning excellence | [5 empty] | #VALUE!
|  | 2.1 Learning facility upgrades - Refurbish additional smart classrooms - Refurbish additional dormitories | Refurbished learning facilities and dormitories | Based on emerging needs, upgrading learning facilities and dormitories of students is required to refurbish available spaces and enhance the learning experience | Additional upgraded learning facilities and dormitories of the Center | 1 | 1.1 | 10000 | Lead, Admin, Tech | X | X | X | [7 empty] | X | X
|  | 2.2 Delivery of short courses - Advertise the short courses - Select trainees - Recruit trainers - Prepare training materials and space - Arrange housing and catering for trainees - Manage travel expense for trainees and visiting professors | To deliver short-term courses essential for therapeutic advancements | CDT-Africa will deliver two short courses (the following courses are provisionally listed as important priorities: 1) Health Research Ethics and Good Clinical Practice, 2) Trial Monitoring, 3) DSMB and Good Laboratory Practice, 4) Proposal Development and Grant Writing, and 5) Clinical Trials Methodology. | 28 trainees completed short courses [28 National (10 Male, 18 Female) | 2 | 2.2 | 12000 | Tech | X | X | X | X
|  | 2.3 Ongoing PhD students support | To support ongoing PhD students already enrolled within the existing PhD programs. | CDT-Africa has 20 PhD fellows emrolled within existing programs of CHS AAU. | 23 PhD Students [21 National (18 M, 3 F), 2 Regional (2 F)] supported. | 2 | 2.2 | 55000 | Lead, Tech, Admin | X | X | X | [6 empty] | X | X | X
|  | 2.4 Ongoing MSc students support | To support ongoing MSc students already enrolled within the existing PhD programs. | CDT-Africa has 26 MSc students enrolled within existing programs of CHS AAU. | 26 MSc Students [21 National (11 M, 10 F), 5 Regional (3 F, 2M] supported. | 2 | 2.2 | 65000 | Lead, Tech, Admin
|  | 2.4 Enrolment of MSc & PhD/Postdoctoral students (including advertisment, enrollment and run programs with respective departments) | To enroll students in MSc in Clinical Trial and PhD in Translational Medicine programs. | CDT-Africa focuses on increasing capacity for therapeutic innovations regionally. As part of this effort, the Center aims to enrol up to 35 students (25 MSc and 10 PhD). | Enrolment of 20 PhD/Postdoctoral Students in 2 rounds [15 National (8 M, 7 F), 5 Regional (3 M, 2 F)] Enrolement of 45 MSc students in 2 rounds [35 National (17 M, 18 F), 10 Regional (5 M, 5 F)] | 2 | 2.2 | 150000 | Lead, Tech, Admin | X | X |  |  |  | X | X | X | X | X | X | X
|  | 2.7 Faculty and PhD students exchanges | To promote research and teaching at CDT-Africa and CHS AAU at large | PhD students and the CDT-Africa/CHS faculty neeed to learn from and adapt therapeutic development skills to apply in their acedemic and research activities | No. of exchanges for CDT-Africa/CHS faculty and students | 2 | 2.6 | 30000 | [7 empty] | X | X | X | X | X | X
|  | Sub-component 3: Research Excellence | [5 empty] | 676000
|  | 3.1 Initiate therapeutic innoviation research projects, preferrably linked to capacity building, e.g. PhD research projects. | To initiate research projects in an area with clear gap of knowledge or guideline on treatment, diagnostics, vaccines, or complex interventions. | The projects will enhance development of medicines, vaccines, diagnostics, or complex interventions. The projects offer opportunity for capacity building. | Three projects initiated - at least the major preparatory steps undertaken; three grant applications submitted | 2 | 2.5 | 10000 | Lead, Tech | X |  | X |  |  |  | X
|  | 3.2 Conduct confirmational pre-clinical study on promising herbal products - Procure reagents, chemicals and animals - Conduct relevant confirmatory study on animals | To confirm safety, efficacy and kinetics of herbal products | Conducting conformational tests in experimental studies on animals is needed to confirm safety, efficacy and kinetics of the product, with preliminary information confirmed and available for translational work and further development including clinical trials in humans. | Herbal products made available for further development including clinical trials in humans. | 2 | 2.5 | 10000 | Lead, Tech | X | X | X | X | X | X | X | X | X | X | X | X
|  | 3.3 Support project development for external small grants | 1) to support skill development for grant writing, 2) Fund rising to support projects | Supports young scholars and PhD students to aquire the skills for writing and securing grants as part of developing independent researchers | Three grant proposals developed and submitted | 2 | 2.5 | 5000 | Lead, Tech, Admin | X | X | X | X | X | X | X | X | X | X | X | X
|  | 3.4 Procure laboratory equipment, reagent and supplies necessary for conducting clinical trials and therapeutic development studies | Organize laboratory and conduct at least three clinical trial and therapeutic development studies | Organizing a laboratory is needed to conduct clinical trials and therapeutic development studies potential drugs, diagnostics and vaccines | Clinical trials and therapeutic development studies are underway and some outcomes presented in conferences | 2 | 2.5 | 650000 | Lead, Tech, Admin | X | X | X | X | X | X | X | X | X | X | X | X
|  | 3.5 Publish research finding in reputable journals | Inform scientific outcomes of the Center | The Center needs to publish study findings to contribute to development of therapeutics at national, regional, and global levels | At least 10 articles ocusing on therapeutic discovery and development, including complex interventions, published in peer-reviewed journals | 2 | 2.5 | 1000 | Lead, Tech | X | X | X | X | X | X | X | X | X | X | X | X
|  | Sub-component 4: Quality assurance | [5 empty] | 68200
|  | 4.1 Quality benchmarking - Identify centers to benchmark - Contact centers and arrange for visit - Conduct site visit - Implement changes - Also explore rrequirements for PASET benchmarking | To adapt implementation according to benchmarked standards | Ensuring quality assurance requires benchmarking three international centers thereby developing implementation framework and standardize accordingly. | Three international centers visited and benchmarked, framework for implementation developed and standardized | 2 | 2.8 | 60000 | Lead, Tech, Admin | X | X | X | [6 empty] | X | X | X
|  | 4.2 Host scientific advisory board and public advisory board meeting - Communicate with Board Members - Secure accommodation for regional and international members - Agree agenda of Meeting - Hold Meeting | To obtain scientific and administrative inputs for the Center | These meetings are required to obtain input on the scientific merit and required improvements on the implementation of CDT-Africa and to obtain public buy-in and accountability of CDT-Africa, and to obtain inputs from the public regarding environmental impact | Obtain guidance and feedback from the boards | 1 | 1.1 | 5100 | Admin |  |  | X |  |  | X |  |  | X |  |  | X
|  | 4.3 Monitoring and evaluation | Monitor and evaluate activities of the Center based on the Center's monitoring and evaluation framework | Continuous monitoring and evaluation of the Center's activities is needed for achieving the objectives of the Center | The Center adhered strictly to best financial, procurement, monitoring and evaluation practices during the entire project | 1 | 1.2 | 3000 | Lead | X | X | X | X | X | X | X | X | X | X | X | X
|  | 4.4 Obtaining national accreditation | To obtain national accreditation of one MSc curriculum in clinical trials | The program's MSc curriculum in clinical trials need to obtain national accreditation | The curriculum recognized by Ministry of Education. Higher Education and Quality Agency (HERQA) approached and HERQA self-assessment completed. | 2 | 2.3 | 100 | Lead, Tech | [8 empty] | X | X | X | X
|  | Sub component 5: Strengthen education & research capacity | [5 empty] | 20500
|  | 5.1 Support faculty to submit major grant applications | To support CDT-Africa and AAU faculty for grant application | The faculty's capacity to developing and submitting grants need to be strengthened; this will also ensure sustainability of CDT-Africa | At least five suitable proposals developed and submitted to donor agencies or potential private sector, and at least one proposal funded | 2 | 2.7 | 20000 | Lead, Tech | X | X | X | X | X | X | X | X | X | X | X | X
|  | 5.2 Raise revenue from external sources | To sustain CDT-Africa through raising revenue from external resources | Generating external revenue is critical to ensure sustainability of programs and projects under the CDT-Africa | External revenue generated | 2 | 2.7 | 500 | Lead, Tech, Admin | X | X | X | X | X | X | X | X | X | X | X | X
|  | Sub component 6: Adhere to best financial management practice | [5 empty] | 4700
|  | 6.1 Prepare and submit annual financial report | To establish a sound financial system | CDT-Africa need to establish a sound financial system that meets all international best practices | Two financial reports submitted by the end of the year. | 3 | 3.1 | 200 | Admin | [5 empty] | X | [5 empty] | X
|  | 6.2 Ensure transparency in financial management - Publish budgets, annual work plans, audit reports, and financial reports on AAU/CDT-Africa website by Months 6 & 12 of the project year | To ensure a sound financial system that meets international best practices | CDT-Africa need to ensure transparency in financial management by uploading budget, annual work plan, audit reports, and financial management plan on its website | Restrictive web-accessible audit and financial reports, annual work plan, and budgets | 3 | 3.4 | 500 | Admin | X | X | X | X | X | X | X | X | X | X | X | X
|  | 6.3 Ensure internal audit oversight - Engage AAU internal audit unit in all financial procedures and transactions. Includes employment of an internal auditor to support CDT-Africa and the College of Health Sciences | Ensure CDT-Africa has internal audit oversight in collaboration with Addis Ababa University | An inclusive internal auditing of the project needs to be conducted at the end of month 12, engaging the AAU internal audit unit. The AAU Finance Directorate will follow due diligence at all stages of the audit. | The internal audit office of AAU conducted inclusive auditing at the end of month 12. | 3 | 3.3 | 4000 | Admin | [11 empty] | X
|  | Sub component 7 : Ensure best procurement practice | [5 empty] | 7000
|  | 7.1 Undertake third-party procurement processes verification | To ensure the enter has a verified procurement process. | CDT-Africa's procurement procedures need to be verified by a third party. | The Center's procurement procedures verified by a third-party. | 4 | 4.2 | 4000 | Admin | [5 empty] | X | X |  |  |  | X | X
|  | 7.2 Ensure timeliness of procurement process | To ensure availability of sound procurement procedures that meet all international standards | Automated procurement procedure in place | Timeliness of all procurement processes and transactions | 4 | 4.1 | 3000 | Admin | X | X | X | X | X | X | X | X | X | X | X | X
|  | Total Component Budget | [5 empty] | #VALUE!
|  | Contingency (5%) | [5 empty] | #VALUE!
|  | Grand total Budget | [5 empty] | 55555
NB: Lead: Center Leadership Unit; Tech: Center Technical Unit; Admin: Center Administration and Operation Unit

## Sheet1
EASTERN AND SOUTHERN AFRICA CENTERS OF EXCELLENCE (ACE II)
Name of the ACE: |  | Center for Innovative Drug Development and Therapeutic Trials for Africa (CDT-Africa) | [7 empty] | Budget Year 2011 E.C, 2018/19 G.C
July 08 2018 - July 07 2019
Component | Sub- component | Action Plan | Objective | Justification | Output | DLI # | DLR # | Estimated Budget (US$) | Responsible Unit | Hamle/ July | Nehase/ August | Meskerem/ September | Tikimt/ October | Hidar/ November | Tahisas/ December | Tir/ January | Yekatit/ February | Megabit/ March | Miyazia/ April | Ginbot/ May | Sene/ June
Component: Strengthening CDT-Africa Center of Excellence
|  | Sub-component 1: Well functioning CDT-Africa Consortium | [5 empty] | 179000
|  | 1.1. Effect salary of existing and new staff of the Center | Staff required to execute day to day activities of the Center | The Center has employed essential staff to support the teaching and research tasks of CDT-Africa. Additional staff staff for the Bio-Hub, Data Manager, Data Entry Clerks and Admin staff. | Having a well staffed Center to deliver on key objectives of CDT Africa | 1 | 1.1 | 120000 | Lead, Tech, Admin | X | X | X | X | X | X | X | X | X | X | X | X
|  | 1.2 Setting up additional office spaces of the Center | To have additional well-organized and functional office space | The Center's existing office space is too small to accommodate all staff and faculty. Thus, the Center plans to secure additional office spaces in AAU and renoviate, refurbish and furnish accordingly. | Additional refurbished office spaces of CDT-Africa | 1 | 1.1 | 50000 | Lead, Tech, Admin | X | X | X | X | X | X
|  | 1.3 Regularly update the Center's website | To regularly communicate status of the Center and use as platform for transfer of scientific knowledges | The website is proved to be an essential platform for information exchange about the CDT-Africa. An expert will be assigned on part-time bases for this task. | Center website updated regularly | 1 | 1.1 | 3000 | Lead, Tech | X | X | X | X | X | X | X | X | X | X | X | X
|  | 1.4 To identify and sign additional MoUs | To identify and signadditional MoUs with potential national and international partners for collaborative undertakings | The Center needs more collaborating institutions to effectivly attain it's objectives | Signed MoUs | 1 | 1.1 | 1000 | Lead, Tech | X | X | X | X | X | X | X | X | X | X | X | X
|  | 1.5 Host annual consortium meeting | CDT-Africa plans to conduct an annual consortum meeting with is partners to update status of the Center and plan activities | CDT-Africa needs to obtain direction from its consortum members for effectiveness | Feedback and plan | 1 | 1.1 | 20000 | Lead, Admin, Tech, |  |  | X | [5 empty] | X
|  | 1.6 Staff development | To strengthen capacity of the Center through capacity development of its staff | Capacity of existing staff needs to be strenthened for effectiveness of the Center | No. of staff gaps identified and capacity developed through training, exchange visits, mentorships | 1 | 1.1 | 20000
|  | 1.7 Maintenance of vehicles cost, Fuel & lubricants | To standby CHS's vehicles for the Center | The Center's vehicles used for office use and to transport students need to have fuel, lubricants, and maintenance for effective use | Uninterrupted transport services | 2 | 1.1 | 5000 | Admin | X | X | X | X | X | X | X | X | X | X | X | X
|  | Sub-component 2: Learning excellence | [5 empty] | 322000
|  | 2.1 Learning facility upgrades - Refurbish additional smart classrooms - Refurbish additional dormitories | Refurbished learning facilities and dormitories | Based on emerging needs, upgrading learning facilities and dormitories of students is required to refurbish available spaces and enhance the learning experience | Additional upgraded learning facilities and dormitories of the Center | 1 | 1.1 | 10000 | Lead, Admin, Tech | X | X | X | [7 empty] | X | X
|  | 2.2 Delivery of short courses - Advertise the short courses - Select trainees - Recruit trainers - Prepare training materials and space - Arrange housing and catering for trainees - Manage travel expense for trainees and visiting professors | To deliver short-term courses essential for therapeutic advancements | CDT-Africa will deliver two short courses (the following courses are provisionally listed as important priorities: 1) Health Research Ethics and Good Clinical Practice, 2) Trial Monitoring, 3) DSMB and Good Laboratory Practice, 4) Proposal Development and Grant Writing, and 5) Clinical Trials Methodology. | 28 trainees completed short courses [28 National (10 Male, 18 Female) | 2 | 2.2 | 12000 | Tech | X | X | X | X
|  | 2.3 Ongoing PhD students support | To support ongoing PhD students already enrolled within the existing PhD programs. | CDT-Africa has 20 PhD fellows emrolled within existing programs of CHS AAU. | 23 PhD Students [21 National (18 M, 3 F), 2 Regional (2 F)] supported. | 2 | 2.2 | 55000 | Lead, Tech, Admin | X | X | X | [6 empty] | X | X | X
|  | 2.4 Ongoing MSc students support | To support ongoing MSc students already enrolled within the existing PhD programs. | CDT-Africa has 26 MSc students enrolled within existing programs of CHS AAU. | 26 MSc Students [21 National (11 M, 10 F), 5 Regional (3 F, 2M] supported. | 2 | 2.2 | 65000 | Lead, Tech, Admin
|  | 2.4 Enrolment of MSc & PhD/Postdoctoral students (including advertisment, enrollment and run programs with respective departments) | To enroll students in MSc in Clinical Trial and PhD in Translational Medicine programs. | CDT-Africa focuses on increasing capacity for therapeutic innovations regionally. As part of this effort, the Center aims to enrol up to 35 students (25 MSc and 10 PhD). | Enrolment of 20 PhD/Postdoctoral Students in 2 rounds [15 National (8 M, 7 F), 5 Regional (3 M, 2 F)] Enrolement of 45 MSc students in 2 rounds [35 National (17 M, 18 F), 10 Regional (5 M, 5 F)] | 2 | 2.2 | 150000 | Lead, Tech, Admin | X | X |  |  |  | X | X | X | X | X | X | X
|  | 2.7 Faculty and PhD students exchanges | To promote research and teaching at CDT-Africa and CHS AAU at large | PhD students and the CDT-Africa/CHS faculty neeed to learn from and adapt therapeutic development skills to apply in their acedemic and research activities | No. of exchanges for CDT-Africa/CHS faculty and students | 2 | 2.6 | 30000 | [7 empty] | X | X | X | X | X | X
|  | Sub-component 3: Research Excellence | [5 empty] | 676000
|  | 3.1 Initiate therapeutic innoviation research projects, preferrably linked to capacity building, e.g. PhD research projects. | To initiate research projects in an area with clear gap of knowledge or guideline on treatment, diagnostics, vaccines, or complex interventions. | The projects will enhance development of medicines, vaccines, diagnostics, or complex interventions. The projects offer opportunity for capacity building. | Three projects initiated - at least the major preparatory steps undertaken; three grant applications submitted | 2 | 2.5 | 10000 | Lead, Tech | X |  | X |  |  |  | X
|  | 3.2 Conduct confirmational pre-clinical study on promising herbal products - Procure reagents, chemicals and animals - Conduct relevant confirmatory study on animals | To confirm safety, efficacy and kinetics of herbal products | Conducting conformational tests in experimental studies on animals is needed to confirm safety, efficacy and kinetics of the product, with preliminary information confirmed and available for translational work and further development including clinical trials in humans. | Herbal products made available for further development including clinical trials in humans. | 2 | 2.5 | 10000 | Lead, Tech | X | X | X | X | X | X | X | X | X | X | X | X
|  | 3.3 Support project development for external small grants | 1) to support skill development for grant writing, 2) Fund rising to support projects | Supports young scholars and PhD students to aquire the skills for writing and securing grants as part of developing independent researchers | Three grant proposals developed and submitted | 2 | 2.5 | 5000 | Lead, Tech, Admin | X | X | X | X | X | X | X | X | X | X | X | X
|  | 3.4 Procure laboratory equipment, reagent and supplies necessary for conducting clinical trials and therapeutic development studies | Organize laboratory and conduct at least three clinical trial and therapeutic development studies | Organizing a laboratory is needed to conduct clinical trials and therapeutic development studies potential drugs, diagnostics and vaccines | Clinical trials and therapeutic development studies are underway and some outcomes presented in conferences | 2 | 2.5 | 650000 | Lead, Tech, Admin | X | X | X | X | X | X | X | X | X | X | X | X
|  | 3.5 Publish research finding in reputable journals | Inform scientific outcomes of the Center | The Center needs to publish study findings to contribute to development of therapeutics at national, regional, and global levels | At least 10 articles ocusing on therapeutic discovery and development, including complex interventions, published in peer-reviewed journals | 2 | 2.5 | 1000 | Lead, Tech | X | X | X | X | X | X | X | X | X | X | X | X
|  | Sub-component 4: Quality assurance | [5 empty] | 68200
|  | 4.1 Quality benchmarking - Identify centers to benchmark - Contact centers and arrange for visit - Conduct site visit - Implement changes - Also explore rrequirements for PASET benchmarking | To adapt implementation according to benchmarked standards | Ensuring quality assurance requires benchmarking three international centers thereby developing implementation framework and standardize accordingly. | Three international centers visited and benchmarked, framework for implementation developed and standardized | 2 | 2.8 | 60000 | Lead, Tech, Admin | X | X | X | [6 empty] | X | X | X
|  | 4.2 Host scientific advisory board and public advisory board meeting - Communicate with Board Members - Secure accommodation for regional and international members - Agree agenda of Meeting - Hold Meeting | To obtain scientific and administrative inputs for the Center | These meetings are required to obtain input on the scientific merit and required improvements on the implementation of CDT-Africa and to obtain public buy-in and accountability of CDT-Africa, and to obtain inputs from the public regarding environmental impact | Obtain guidance and feedback from the boards | 1 | 1.1 | 5100 | Admin |  |  | X |  |  | X |  |  | X |  |  | X
|  | 4.3 Monitoring and evaluation | Monitor and evaluate activities of the Center based on the Center's monitoring and evaluation framework | Continuous monitoring and evaluation of the Center's activities is needed for achieving the objectives of the Center | The Center adhered strictly to best financial, procurement, monitoring and evaluation practices during the entire project | 1 | 1.2 | 3000 | Lead | X | X | X | X | X | X | X | X | X | X | X | X
|  | 4.4 Obtaining national accreditation | To obtain national accreditation of one MSc curriculum in clinical trials | The program's MSc curriculum in clinical trials need to obtain national accreditation | The curriculum recognized by Ministry of Education. Higher Education and Quality Agency (HERQA) approached and HERQA self-assessment completed. | 2 | 2.3 | 100 | Lead, Tech | [8 empty] | X | X | X | X
|  | Sub component 5: Strengthen education & research capacity | [5 empty] | 20500
|  | 5.1 Support faculty to submit major grant applications | To support CDT-Africa and AAU faculty for grant application | The faculty's capacity to developing and submitting grants need to be strengthened; this will also ensure sustainability of CDT-Africa | At least five suitable proposals developed and submitted to donor agencies or potential private sector, and at least one proposal funded | 2 | 2.7 | 20000 | Lead, Tech | X | X | X | X | X | X | X | X | X | X | X | X
|  | 5.2 Raise revenue from external sources | To sustain CDT-Africa through raising revenue from external resources | Generating external revenue is critical to ensure sustainability of programs and projects under the CDT-Africa | External revenue generated | 2 | 2.7 | 500 | Lead, Tech, Admin | X | X | X | X | X | X | X | X | X | X | X | X
|  | Sub component 6: Adhere to best financial management practice | [5 empty] | 4700
|  | 6.1 Prepare and submit annual financial report | To establish a sound financial system | CDT-Africa need to establish a sound financial system that meets all international best practices | Two financial reports submitted by the end of the year. | 3 | 3.1 | 200 | Admin | [5 empty] | X | [5 empty] | X
|  | 6.2 Ensure transparency in financial management - Publish budgets, annual work plans, audit reports, and financial reports on AAU/CDT-Africa website by Months 6 & 12 of the project year | To ensure a sound financial system that meets international best practices | CDT-Africa need to ensure transparency in financial management by uploading budget, annual work plan, audit reports, and financial management plan on its website | Restrictive web-accessible audit and financial reports, annual work plan, and budgets | 3 | 3.4 | 500 | Admin | X | X | X | X | X | X | X | X | X | X | X | X
|  | 6.3 Ensure internal audit oversight - Engage AAU internal audit unit in all financial procedures and transactions. Includes employment of an internal auditor to support CDT-Africa and the College of Health Sciences | Ensure CDT-Africa has internal audit oversight in collaboration with Addis Ababa University | An inclusive internal auditing of the project needs to be conducted at the end of month 12, engaging the AAU internal audit unit. The AAU Finance Directorate will follow due diligence at all stages of the audit. | The internal audit office of AAU conducted inclusive auditing at the end of month 12. | 3 | 3.3 | 4000 | Admin | [11 empty] | X
|  | Sub component 7 : Ensure best procurement practice | [5 empty] | 7000
|  | 7.1 Undertake third-party procurement processes verification | To ensure the enter has a verified procurement process. | CDT-Africa's procurement procedures need to be verified by a third party. | The Center's procurement procedures verified by a third-party. | 4 | 4.2 | 4000 | Admin | [5 empty] | X | X |  |  |  | X | X
|  | 7.2 Ensure timeliness of procurement process | To ensure availability of sound procurement procedures that meet all international standards | Automated procurement procedure in place | Timeliness of all procurement processes and transactions | 4 | 4.1 | 3000 | Admin | X | X | X | X | X | X | X | X | X | X | X | X
|  | Total Component Budget | [5 empty] | 1277400
|  | Contingency (5%) | [5 empty] | 63870
|  | Grand total Budget | [5 empty] | 55555
NB: Lead: Center Leadership Unit; Tech: Center Technical Unit; Admin: Center Administration and Operation Unit